Meeting of the National Coordinators of the DIHK – ABC Project and the ABC Working Group on Sustainability

07th – 08th October, 2008, Sarajevo, Bosnia & Herzegovina

P R O T O C O L

Aim:	The national coordinators of the DIHK – ABC Project meet for their second annual meeting to make an overview of the  fulfilled activities from the Agenda for 2008 and to discuss and prepare the activities to be done till the end of the year. They also meet to prepare the Concept for Sustainability that is to be presented at the next ABC General Assembly on 27.11.2008 in Istanbul.

Main topics:

- Activity Overview 2008

- Upcoming activities till the end of 2008

- Ideas for activities in 2009

- Contribution to the Concept for Sustainability

Discussions:

- Activity Overview 2008

Each of the coordinators expressed their impressions on the activities done in 2008 till the moment of the meeting. The biggest event for 2008 – the meeting of the ABC Presidents with the TOP Management of the DIHK, held in Berlin on 09.-11.04.2008 was talked over with details and attention. The weak and strong points of this event were thoroughly discussed in order to find new ways for future cooperation more targeted towards the Western Balkan chambers.

More details are given in the table Activity Overview till October, 2008, enclosed to this Protocol.

- Upcoming activities till the end of the 2008

  - Meeting of the IT WG – 11. – 13.11.2008, Montenegro

Deadline for confirmation: 15.10.2008.

  - Balkan Summit and ABC General Assembly – 26.-27.11.2008, Istanbul

The Turkish coordinator Mrs. Füsun Karacasoy gave individual official letter, invitations and draft programs to all the presenting ABC chambers. The respective ministers and speaker from the ABC countries will be invited by TOBB.

  - ABC Info Stand at the Fair Ethno Food  - 26.-29.11.2008, Belgrade

This stand of 50 m 2 will be arranged only as info stand. Companies from all the ABC countries can expose their information and PR materials and samples, but cannot send their representative at the stand. The stand must contain the logos of ABC, DIHK, BMZ, SEQUA. All kinds of materials, brochures, leaflets, etc of the ABC should be exposed their. Furthermore the Project can cover the hotel accommodation for up to 2 representatives of the ABC beneficiary chambers for their presence at the stand in order to give information about the food market condition in their countries and in the region.

  - Sector-specific cooperation meetings between ABC and Germany

Postponed for 2009. CCI Frankfurt expressed interest to host this activity and will announce later which sectors are of interest to them.

  - Brochure on Chamber Service of the Chamber of Economy of Macedonia – will be finished till the end of 2008

  - Training on Services of the Educational Department of CCI Gera for an expert from Montenegro Chamber – will be done

  - Seminar for companies on EU technical Regulations in the Construction Sectors  - will be done in Montenegro

  - Consulting on Preparation of EU project within ABC – will be done in Serbia

  - Link “ Investment on the Balkans” on the ABC portal www.abcinfos.com – The CCIR to open this link on the portal and every chamber to upload their national links on the topic

  - Further development of the ABC portal www.abcinfos.com – will to be done in each ABC chamber

  - Brochure “Balkan Fairs and Exhibitions 2009” – will be done in Bulgaria

  - Presentation of the German market and Opportunities for ABC / CEFTA companies – will be done in B & H

Sectors: Metal processing; Food industry; Wood processing; Textile industry; Furniture industry

More details are given in the table Activities to be done till the end of 2008, enclosed to this Protocol.

- Ideas for activities in 2009

  - National Coordinators’ meeting in Sofia – end of January, beginning of February

  - 2nd National Coordinators’ Meeting in Turkey beginning of October

  - Sector specific cooperation meetings between ABC Germany in Frankfurt

  - Seminars on EU Customs Regulations and Preferential System (Mr. Berndt) - in Serbia, Macedonia, Montenegro, B & H and ? Romania?

  - ? Training in Germany on Foreign Economic Relations and Multilateral Cooperation?

  - ? Training on Social Dialogue and Development of Chamber role – Best practices – Bulgaria, Turkey, Brussels - in Macedonia?

  - Training on OHSAS 18001 – in Macedonia

  - Educational training session on QMS for the staff of the Montenegro Chamber

  - Seminar on Income Generating Activities

  - Consultancy mission in Macedonia

  - ABC Summer Academy –in Chalkidiki, Greece

  - Training in Germany for 1 ABC expert

  - ABC General Assembly – in Albania

  - Meeting of the IT WG – in Romania

  - Trade mission of Serbian companies from the construction business to Romania

  - Conference in Macedonia

  - CD on Investment and trade Opportunities in the Western Balkans - contact information, company profiles, investment projects, etc.

- Contribution to the Concept for Sustainability

3 parts of the Contribution to the Concept for Sustainability:

1. Contents:	 What kind of activities

2. Organization:  Tasks, time, place and responsible chamber

3. Financing: by own funds or by applying for on different EU programs, initiatives, projects or EUROCHAMBRES

| No. | Contents | Organization |  |  |  | Financing |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Tasks | When | Where | Who is responsible |  |
| 1. | Meeting of the National Coordinators | To elaborate an annual activity agenda | Minimum once per year | In accordance with the rotating system of the ABC Presidency | The ABC Presidency CCI | Option 1: during the ABC General Assembly  no need of extra expenses Option 2: separate meeting  transport, hotel and daily allowance expenses covered by each CCI participating; rent for hall covered by the hosting CCI |
| 2. | Regular Meetings of the ABC Working Groups on EU Integration, Trade Facilitation and IT | 1. to elaborate strategy papers and to present it to the ABC GA in order to influence the governments towards EU issues 2. to enhance the cooperation with other institutions, associations, etc. | Before the ABC GA in order the strategy papers to be included in the Agenda of GA | By the decision of the WG members | EU Integration – Greece Trade Facilitation – Serbia IT – Romania | Transport, hotel and food expense covered by each CCI participating; rent for hall covered by the hosting CCI |
| 3. | Further development of the ABC portal www.abcinfos.com | To maintain the portal as a common product of the ABC | Continuously | Romania | Romania | Romania |
| 4. | Common ABC stands on fairs and exhibitions | 1. to promote the cooperation between the ABC company between themselves and between them and third parties 2. to promote the ABC as institution by providing information, PR materials, leaflet, brochure, etc. | By the decision of the National Coordinators | In accordance with the rotating system of the ABC Presidency | The ABC Presidency CCI | The ABC Presidency CCI covers the expenses for the stand OR invite national companies upon participation fee |
| 5. | Matchmaking cooperation meetings | To enhance cooperation, trade and investment opportunities within the ABC countries and with third parties | Once per year | By the decision of the National Coordinators | The hosting chamber | By participation fee from the companies |
| 6. | Business conference | 1.To enhance cooperation, trade and investment opportunities within the ABC countries and with third parties 2. to promote the ABC as institution 3. to provide forum for exchanging ideas, proposal, initiatives, etc. | Once per year | In accordance with the rotating system of the ABC Presidency | The ABC Presidency CCI | By participation fee, sponsors or other project |
| 7. | Trainees between the ABC CCI | To exchange know-how, experiences, information about the different systems, organization, work, etc. | By the decision of the National Coordinators | By the decision of the National Coordinators | The hosting CCI | the CCI sending a trainee covers the expenses for the training (transport, hotel, daily allowance, honorary for the trainer, is requested) |
| 8. | Seminars and workshops for chamber staff and / or companies | 1.To provide better services for chamber member 2. to improve the qualification of the chamber staff | 1 to 3 seminars per year | By the decision of the National Coordinators | The hosting chamber sends invitation to the other chambers and to its national companies. the other chambers send invitations to their national companies, who by interest confirm directly to the hosting chamber | By participation fee, sponsors or other project |

Participated:

- Mr. Eduard Schwartz (leader)		Head of the DIHK-ABC Project

- Mrs. Nermana Bicakcic		FT B&H

- Mrs. Ljubica Nuri			EC Macedonia

- Mrs. Tamara Milunovic		CE Montenegro

- Mrs. Rodica Bodnariuc		CCIR

- Mrs. Snezana Raseta-Pekovic	SCC

- Mrs. Füsun Karacasoy		TOBB

- Mrs. Vanya Toneva			DIHK-ABC Project

- Mr. Karmen Vranchev			DIHK-ABC Project